## Project Timeline
California Department of Transportation Transportation Planning Grants Fiscal Year 2017-2018 PROJECT TIMELINE
| Project Title | Capital Region Transportation Sector Urban Heat Island Mitigation | [14 empty] | Grantee | [6 empty] | Sacramento Metropolitan Air Quality Management District (SMAQMD)
|  | Fund Source |  |  |  |  | Fiscal Year 2017/18 | [11 empty] | FY 2018/19 | [11 empty] | FY 2019/20
Task Number |  | Responsible Party | Total Cost | Grant Amount | Local Cash Match | Local In-Kind Match | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | Deliverable
1 | Project Initiation and Management
1.1 | Initial meeting with Caltrans | SMAQMD | 280 | 210 | 70 | [37 empty] | Meeting notes summary
1.2 | Contract with Sub-Applicant | SMAQMD | 470 | 400 | 70 | [37 empty] | Copy of executed subcontract
1.3 | Request for Proposals and Contracting with Consultants | LGC | 4230 | 3810 | 420 | [37 empty] | Copy of procurement procedures and executed consultant contracts
1.4 | Project Kickoff Meeting | SMAQMD | 1290 | 1080 | 210 | [37 empty] | Meeting agendas; meeting note summaries; participant lists
1.5 | Project Management | SMAQMD | 18775 | 16535 | 2240 | [37 empty] | Meeting notes
1.6 | Technical Advisory Committee | LGC | 19290 | 9130 | 1400 | 8760 | [36 empty] | Meeting agendas; meeting note summaries; participant lists
2 | Community Outreach and Engagement
2.1 | Community Engagement Plan | LGC | 19190 | 10805 | 1155 | 7230 | [36 empty] | Community Engagement Plan; notes from listening sessions; summary of literature review
2.2 | Community Engagement | LGC | 34720 | 30940 | 3180 | 600 | [36 empty] | Workshop agendas; workshop notes; participant lists
2.3 | Community Priorities Report and Map | LGC | 9300 | 7415 | 1885 | [37 empty] | Community Priorities Report; Community Priorities Map
3 | Advanced Urban Heat Island Effect Analysis
3.1 | Land-use and land-cover analysis | Technical Consultant | 22591.21 | 20000 | 2591.21 | [37 empty] | Summary of land-use and land-cover analysis
3.2 | Observational data preparation | Technical Consultant | 22591.21 | 20000 | 2591.21 | [37 empty] | Summary of data analyzed
3.3 | Base atmospheric modeling and model performance evaluation | Technical Consultant | 38405.06 | 34000 | 4405.06 | [37 empty] | Reference-state modeled meteorology for current climate
3.4 | Atmospheric modeling of scenarios and mitigation measures in current climate | Technical Consultant | 89773 | 78600 | 2413 | 8760 | [36 empty] | Atmospheric modeling of current climate and current land-use and land-cover; characterization of mitigation measures; scenarios for current climate
3.5 | Atmospheric modeling of scenarios and mitigation measures in future climate | Technical Consultant | 30000 | 30000 | [38 empty] | Atmospheric modeling of future climate and future land-use and land-cover; scenarios for future climate
3.6 | UHI Analysis Report | Technical Consultant | 20000 | 20000 | [38 empty] | UHI Analysis Report; GIS or Google Earth data; datasets
4 | Regional Transportation Database
4.1 | Compile existing transportation plans and projects | SMAQMD | 44700 | 34550 | 9200 | 950 | [36 empty] | List of transportation projects and plans compiled
4.2 | Assess electric vehicle ownership and infrastructure projections | SMAQMD | 23255 | 9450 | 9425 | 4380 | [36 empty] | Summary of electric vehicle scenarios and their impacts and vulnerabilities to heat
4.3 | Develop Regional Transportation Database and Map | Planning Consultant | 20160 | 19110 | 1050 | [37 empty] | Regional Transportation Database; GIS or Google Earth Map
5 | Regional Heat Pollution Reduction Plan
5.1 | Draft Regional Heat Pollution Reduction Plan | Planning Consultant | 78665 | 55150 | 4675 | 18840 | [36 empty] | Draft Regional Heat Pollution Reduction Plan
5.2 | Finalize Regional Heat Pollution Reduction Plan | Planning Consultant | 17745 | 16110 | 1635 | [37 empty] | Final Regional Heat Pollution Reduction Plan
6 | Integration and Dissemination of Project Results
6.1 | Develop targeted recommendations for local jurisdictions | Planning Consultant | 67688 | 55700 | 11988 | [37 empty] | Targeted local jurisdiction recommendations and template language
6.2 | Develop Project Summary Report | LGC | 12020 | 6950 | 1125 | 3945 | [36 empty] | Project Summary Report
6.3 | Hold webinar(s) and one in-person event | LGC | 2625 | 2250 | 375 | [37 empty] | Webinar(s); participant list(s)
6.4 | Develop case study for ICARP | LGC | 1863 | 1300 | 563 | [37 empty] | Case study for ICARP
7 | Administration
7.1 | Invoicing | SMAQMD | 2700 | 2140 | 560 | [37 empty] | Quarterly invoices to Caltrans
7.2 | Reporting | SMAQMD | 2700 | 2140 | 560 | [37 empty] | Quarterly reports for Caltrans
| TOTALS |  | 605026.48 | 487775 | 63786.48 | 53465
Reimbursement of indirect costs is allowable upon approval of an Indirect Cost Allocation Plan for each year of project activities. Provide rate if indirect costs are included in the project budget. Approved Indirect Cost Rate: ______%
Note: Each task must contain a grant amount and a local cash match amount. Local cash match must be proportionally distributed by the same percentage throughout each task. Local in-kind match needs to be indicated where in-kind services will be used. Please review the grant program section that you are applying to for details on local match requirements. The project timeline must be consistant with the scope of work.